## Checklist
UTILITY COORDINATION
MILESTONE CHECKLIST |  |  |  |  | Date:
Project Name: |  |  |  |  | Project ID:
Project County: |  | Project Type: |  |  | Project Manager:
# | Task |  | Responsible Party | Target Date | Complete | Date Completed
1 | Project Programmed in P2S |  | PM
2 | Pull Utility Inventory from SC 811 DM/ Desktop Google Earth scoping of Utilities PM |  | DM/PM
3 | Submit Design Ticket with SC811 to mark Utilities in the field for Scoping Meeting |  | DM
4 | Initial Field Scoping Meeting / Coordinate SUE determination w/ DM,UC & RCE |  | PM
5 | Verify Utilities in the Field - Add to Scope |  | PM
6 | Consult with State Utility Engineer to identify major/complex utility issues |  | PM
7 | Set Up Utility Coordination Plan and/or Consultant Scope |  | PM
8 | Set up Initial Utility Conflict Management Spreadsheet (UCM) on Projectwise |  | PM
9 | Request that UC request Major Utility Plans and/or Records |  | DM
10 | Prepare SUE Determination Memo & Establish Planning Level Utility Budget |  | PM
11 | Prepare and Distribute Project Scope, Schedule & Budget |  | PM
12a | Request that State Utility Engineer initiate Introduction letter |  | PM
12b | State Utility Engineer sends all Utility Companies a Project Introduction letter (assign Point of Contact/UC/Consultant/PM) |  | State Utility Engineer
13 | Submit SUE and Survey Request to Surveys (determine if special requests for survey gas markers or man hole depths should be included) |  | DM
14 | Review Survey & SUE files; Update UCM |  | DM
15 | Request additional information from Utility Company through UC, if necessary |  | DM
16 | Coordinate with State Utility Engineer for Estimated Costs of Utility Impacts |  | PM
17 | Provide preliminary utility impacts/costs in the NEPA Alternatives Analysis |  | PM
18 | Consider UT impacts in the Alternatives Analysis; AVOID impacts if possible |  | PM
19 | Request UC contact Utility companies if necessary to obtain additional information (clearance requirements/constraints) or set up individual Utility Company meetings if major conflicts anticipated and more info needed. |  | PM
20 | Review Preliminary Plans with DM for Potential Conflicts & Update UCM |  | PM/DM
21 | Design Field Review (DFR); consider UC inviting major utilities with impacts |  | PM/DM
22 | Investigate whether any adjustments can be made in design at DFR to MINIMIZE impacts; request that Utility Company pot hole or mark utilities at DFR if necessary. Explore protective alternatives. Determine whether any utility work would impact/involve environmental permits. |  | DM
23 | Coordinate with ESO on the potential utility relocations located within the SCDOT ROW and whether there is an opportunity to include utility relocation work within the permit. All in contract relocations should be included in the SCDOT permit. Discuss level of details needed for permit application (new utility alignment, size, and construction methods) |  | PM
24 | Once Preliminary ROW plans are available; request UC set up advanced utility coordination meeting to discuss major impacts. Prepare exhibits showing the impacts on the cross sections, if possible. Don't forget to include geotechnical work and/or any normal construction methods (silt fence post, etc.) |  | PM
25 | Secure all preliminary utility relocation or conflict resolution details at this preliminary meeting, including ROW, permitting and schedules. Determine meeting/deliverable schedule for final coordination. |  | UC
26 | Update UCM and Utility Coordination Plan. Determine if any utility companies will be included in construction contract work and/or permits. |  | PM
27 | Issue Final ROW plans to UC for initiation of final Utility Coordination; UC to set up regular Utility Meetings according to Utility Coordination Plan for project. UC to update UCM after each meeting with updated information. |  | DM
28 | Coordinate final deliverables, MITIGATE conflicts through relocation plans, through regular Utility Coordination Meetings. Coordinate with RCE to perform Constructability review of the Utility relocations at the Coordination meetings in order to determine the phasing and timing of all planned utility relocations. |  | UC
29 | Secure all final utility deliverables at least 150 days prior to LET date. |  | UC
30 | Coordinate review of final relocation plans, agreements & permits. |  | UC
31 | Submit final packages to State Utility Engineer for Final Review & Approval at least 150 days prior to the LET date. |  | UC
32 | Coordinate with PM for recommendation and preparation of Utility & Railroad Certification. |  | State Utility Engineer
33 | Utility Ready to Construct. Utility Certification Signed. |  | State Utility Engineer
*If consultant services are utilized on the project, then tasks 8-11 & 12-32 would be delegated to the consultant team.
PM | Program Manager
DM | Design Manager or Designee
UC | Utility Coordinator
RCE | Resident Construction Engineer
ESO | Environmental Services Office
UCM | Utility Conflict Management Spreadsheet

## UCM Summary
Utility Conflict Management (UCM) Matrix
| PROJECT ID: | [6 empty] | COUNTY: | [6 empty] | Scroll right to see attachments >>>
Project Name: | [7 empty] | Updated By:
Description: | [7 empty] | Date Last Update:
Route/Highway: | [7 empty] | UT Deliverable DUE date:
811 Ticket Submitted: | [7 empty] | USACE Permit DUE date: |  |  |  | *due date for utility relocation alignment & construction methods
for those utility relocations being included in SCDOTs Permits
Utility / Contact | Utility Type | Size & Material | General Location | Prior Rights Y/N | Utility Clearance Requirements / Constraints | Utility Conflict Description | SUE Req'd Y/N | Potential Resolution of Conflict | Deliverable | Anticipated Submittal Date | Relocation Work Schedule | USACE Permit Req'd Y/N | ROW Phase Req'd Y/N | In Contract Work Y/N | Utility Window Req'd Y/N | Special Provision Req'd Y/N | Resolution Status Notes
Field / Column |  |  | Description
Utility / Contact |  |  | Name of Utility Owner and/or Point of Contact who has responsibility for the utility facility located within the project
Utility Type |  |  | Type of Utility Facilit, see drop down list
Size & Material |  |  | Size of Utility and/or material of utility facility, example 8" PVC
General Location |  |  | General description of the location of the utility facility on the termini of the project either using stations or milepoints
Prior Rights Y/N |  |  | Estimation or Determination of Prior Rights for the Utility Facility (Does Utility have an underlying property interest at location
Utility Clearance Requirements/Constraints |  |  | Description of any vertical or horizantal clearances required for the utility facility and/or constraints on location or relocation
Utility Conflict Description |  |  | Description of the potential utility conflict with proposed roadway and/or roadway appertenances or construction activities
SUE Required Y/N |  |  | Determination of whether additional SUE data collection is reccomended in order to get more precision on utility location
Potential Resolution of Conflict |  |  | Description of the potential resolution/solution (adjust design, protect, relocate)or the next step to resolve a utility conflict
Deliverable |  |  | The type of utility documentation that will be required as a deliverable in order to confirm the utility coordination resolution
Anticipated Submittal Date |  |  | Anticipated submittal date of the utility documentation deliverable as indicated by the Utility Owner
Relocation Work Schedule |  |  | Estimated date of proposed utility relocation work to occur including utility relocation work initiation date and duration of utility construction
USACE Permit Required Y/N |  |  | Determination of whether a USACE permit for impact to wetlands will be required for the utility construction activities
ROW Phase Required Y/N |  |  | Determination of whether a ROW phase of work would be required for the Utility to secure property on which to relocate their utility
In Contract Work Y/N |  |  | Determination of whether the utility owner would like to include the proposed Utility Relocation work in SCDOT's construction contract
Utility Window Required Y/N |  |  | Determination of whether the utility owner would like to have SCDOT include a Utility Window in the SCDOT construction contract (Note requested time frame in the notes section)
Special Provision Required Y/N |  |  | Determination of whether the utility owner has provided or requested a special provision relating to the utility facility construction needs to be outlined in the proposal
Resolution Status Notes |  |  | Status of the Resolution of the utility conflict as of the date of the UCM being prepared or updated

## Resolution Alternatives
Utility Conflict Management (UCM) - Analysis of Utility Conflict Resolution Alternatives
Utility Conflict ID | Alternative Number | Alternative Description | Alternative Advantages | Alternative Disadvantages | Impact on Project Delivery Time (Months) | Engineering Cost (Utility) | ROW Cost (Utility) | Direct Cost (Utility) | Engineering Cost (DOT) | Direct Cost (DOT) | Other Costs | Total Cost (Utility) | Total Cost (SCDOT) | Feasibility | Decision
Column |  |  | Description
Utility Conflict ID |  |  | Identification for the conflicts as identified for this utility within this resolution analysis
Alternative Number |  |  | Utility Conflict resolution alternative identification number
Alternative Description |  |  | Description of the utility conflict resolution alternative
Alternative Advantages |  |  | Potential advantages associated with the utility conflict resolution alternative
Alternative Disadvantages |  |  | Potential disadvantages associated with the utility conflict resolution alternative
Impact on Project Delivery Time (months) |  |  | Total potential impact of the utility conflict resolution alternative on project delivery time
Engineering Cost (Utility) |  |  | Estimated engineering cost to the utility owner if the utility conflict resolution alternative is selected
Direct Cost (Utility) |  |  | Estimated direct cost to the utility owner if the utility conflict resolution alternative is selected
Engineering Cost (SCDOT) |  |  | Estimated engineering cost to the DOT if the utility conflict resolution alternative is selected
Direct Cost (SCDOT) |  |  | Estimated direct cost to the DOT if the utility conflict resolution alternative is selected
Other Costs |  |  | Other costs if the utility conflict resolution alternative is selected
Total Costs |  |  | Sum of all estimated costs
Feasibility |  |  | Indicator if the utility conflict resolution alternative is feasible or not.
Decision |  |  | Indicator of the status of the utility conflict resolution alternative, see drop down list.

## Final Deliverables Tracking
Utility Deliverables Outstanding/Action Items
Utility Owner | Relocation Plans | Utility Agreements & Documentation | Buy America Certifications | SCDOT Encroachment Permit | Utility Easement Encroachment Permits | UTILITY PACKAGE COMPLETE | Construction Start | Duration | Comments
SCDOT Final Approval Items:
Encroachment Permits | DATE Approved | Utility Agreements | DATE Approved |  |  |  |  | Utility Company Deliverables DUE date:

## Construction Timeline
Utility Relocation Construction Timelines
Utility Owner | Lead Time | Total Duration | Total Time | Predecessor Utility (if applicable) | Notification Date | Start Date | Completion Date
* Utility is dependent on another relocation to be completed before they can initiate relocation; other utility identified in the Predecessor Column.
**Set Dates per relocation contract.

## UT Detail Worksheet
Individual Utility Detailed Conflict Management Report
POTENTIAL CONFLICT LOCATION | [5 empty] | OFFSET |  | CONFLICTS |  | UTILITY |  |  |  | Conflict Description | Resolution/Action | REQUIREMENTS
Location | Start Station | End Station | Plan Sheet Reference | Utility Investigation Level Needed | Test Hole # | Distance (feet) | Side | Roadway Item in Conflict | Utility Item in Conflict | Invert Elevation | Top of Pipe | Depth (ft) | Side | GREEN - No Conflict BLACK - Borderline within 1 ft RED - Confirmed Conflict | BLUE - Adjust Drainage Design ORANGE - Utility Line Adjust/Protect - Utility Line Relocate/Replace | Soft Dig = A | Remarks
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved
[14 empty] | Not Determined | Unresolved

## Drop Down Lists
Drop Down Lists
Utility Type
Communications
Overhead Electric
Underground Electric
Gas Distribution
Pressurized Gas
Transmission
Oil
Sanitary Sewer Gravity
Sanitary Sewer Force
Steam
Storm Sewer
Water
Unknown
Utility Deliverable
No Conflict Letter
No Cost Letter & Relocation Plan
No Cost Letter, FPA & PS&E Package
Utility Agreement & Relocation Plan
Utility Agreement & PS&E Package
Unknown
Utility Investigation Quality Level
QLA
QLB
QLC
QLD
Undetermined
Resolution Status
Utility conflict created
Utility owner informed of utility conflict
Utility conflict resolution strategy selected
Utility conflict resolved
Feasibility
Yes
No
Unknown
Decision
Under Review
Selected
Rejected
Conflict Description
Not Determined
No Conflict
Borderline within 1 ft
Confirmed Conflict
Resolution Action
Unresolved
Adjust Drainage Design
Utility Line Adjust/Protect
Utility Line Relocate/Replace