## Pipe Summary
Inspection Date | Mainline Pipe ID | Column1 | Size | Material | Length | Problems | Solution | Column2 | Reasons
2020-01-09 | EP- | 1839 | 18" | RCP | 279.7 | Yes | Clean and Line |  | • Minor transverse cracking (<12"), Minor chips at joints, all issues are with joint offsets
2020-01-09 | EP- | 1840 | 18" | RCP | 181.7 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major transverse cracking (> 12"), major chips, all other issues are with joint offsets
2020-01-09 | EP- | 1841 | 18" | RCP | 449.5 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), surface damage, root in pipe, all other issues are with joint offsets
2020-01-09 | EP- | 1843 | 18" | RCP | 70.8 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets
2020-01-09 | EP- | 1844 | 18" | RCP | 118 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets • Pipe not listed in overall pipe summary provided by AET
2020-01-09 | EP- | 2407 | 24" | RCP | 243.8 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), Root in pipe, all other issues are with joint offsets
2020-01-09 | EP- | 2408 | 24" | RCP | 115.1 | Yes | Clean and Line |  | • Minor transverse cracking (<12"), all other issues are with joint offsets
2020-01-09 | EP- | 2409 | 24" | RCP | 18.1 | No | Retain |  | • No major issues in pipe
2020-01-09 | EP- | 2413 | 24" | RCP | 55.3 | Yes | Clean and Line |  | • Minor transverse cracking (< 12"), all other issues are with joint offsets
2020-01-15 | EP- | 1837 | 18" | RCP | 125.3 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-15 | EP- | 1838 | 18" | RCP | 321.4 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets
2020-01-15 | EP- | 1838.1 | 18" | RCP | 321.4 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major chips at joints, all other issues are with joint offsets • Pipe not listed in overall pipe summary provided by AET
2020-01-15 | EP- | 1845.1 | 18" | RCP | 113.9 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-15 | EP- | 1846 | 18" | RCP | 115.1 | Yes | Clean and Line |  | • Major chips at joints, all other issues are with joint offsets
2020-01-15 | EP- | 1847 | 18" | RCP | 119.2 | Yes | Clean and Line |  | • Minor chips at joints, all other issues are with joint offsets
2020-01-15 | EP- | 1848 | 18" | RCP | 109.8 | Yes | Clean and Line |  | • Minor transverse cracking (<12"), Debris in pipe, all other issues are with joint offsets
2020-01-15 | EP- | 1849 | 18" | RCP | 110.1 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major transverse cracking (> 12"), major chips at joints, debris in pipe, all other issues are with joint offsets
2020-01-15 | EP- | 2410 | 24" | RCP | 92.8 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-15 | EP- | 2411 | 24" | RCP | 114.3 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-15 | EP- | 2412 | 24" | RCP | 123.9 | Yes | Clean and Line |  | • Minor transverse cracking (< 12"), all other issues are with joint offsets
2020-01-15 | EP- | 4804 | 48" | RCP | 133 | Yes | Clean and Line |  | • Major transverse cracking (>12")
2020-01-15 | EP- | 4805 | 48" | RCP | 126.2 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), surface damage, all other issues are with joint offsets and gaskets
2020-01-15 | EP- | 4806 | 48" | RCP | 291.3 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), surface damage, all other issues are with joint offsets and gaskets
2020-01-15 | EP- | 4807 | 48" | RCP | 324.5 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
2020-01-15 | EP- | 4808 | 48" | RCP | 310.3 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), joint infiltration
2020-01-16 | EP- | 1001 | 18" | RCP | 68.8 | Yes | Replace |  | • Major chips/broken areas within the pipe
2020-01-16 | EP- | 1501 | 15" | RCP | 129.6 | Yes | Clean and Line |  | • Minor transverse cracking (< 12"), all other issues are with joint offsets
2020-01-16 | EP- | 1503 | 15" | RCP | 167.8 | Yes | Replace |  | • Major chips in the pipe as well as cracking. Rebar also showing in some locations
2020-01-16 | EP- | 1504 | 18" | RCP | 16.8 | No | Retain |  | • No major issues in pipe
2020-01-16 | EP- | 1832 | 18" | RCP | 14.9 | Yes | Clean and Line |  | • Minor chip at the joint
2020-01-16 | EP- | 1833 | 18" | RCP | 88.6 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chip at 1 joint • Major cracking (> 12"), major chip at 1 joint, all other issues are with joint offsets
2020-01-16 | EP- | 1834 | 18" | RCP | 58 | Yes | Replace |  | • Pipe broken at 1 joint, all other issues are with joint offsets
2020-01-16 | EP- | 1835 | 18" | RCP | 31.5 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-16 | EP- | 1836 | 18" | RCP | 42.8 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-16 | EP- | 1850 | 15" | RCP | 113.2 | Yes | Clean and Line |  | • Minor transverse cracking (<12"), all other issues are with joint offsets
2020-01-16 | EP- | 1850 | 18" | RCP | 113.2 | Yes | Clean and Line |  | • Major chips, Major transverse cracking (> 12"), all other issues are with joint offsets • Pipe not listed in overall pipe summary provided by AET
2020-01-16 | EP- | 1851 | 18" | RCP | 112.7 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major chips, Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 1852 | 18" | RCP | 126.6 | Yes | Replace |  | • Major chips, Major transverse cracking (> 12"), broken areas within the pipe, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 1852.1 | 18" | RCP | 138.4 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), Debris in pipe, all other issues are with joint offsets
2020-01-16 | EP- | 2402 | 24" | RCP | 54.3 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-16 | EP- | 2403 | 24" | RCP | 31.2 | Yes | Clean and Line |  | • Major chip at one joint, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 2404 | 24" | RCP | 25.2 | Yes | Clean and Line |  | • All issues are with joint offsets
2020-01-16 | EP- | 2405 | 24" | RCP | 128.5 | Yes | Replace |  | • Broken areas within the pipe, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 2414 | 24" | RCP | 47.9 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to chip/exposed rebar at one joint • Major transverse cracking (> 12"), exposed rebar, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 2415 | 24" | RCP | 65.8 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major cracking at one joint • Major cracking (> 12"), all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 2416 | 24" | RCP | 68.8 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), debris in pipe, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 3001 | 24" | RCP | 80.3 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 4803 | 48" | RCP | 63.8 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), surface damage, all other issues are with joint offsets and gaskets
2020-01-16 | EP- | 4809 | 48" | RCP | 233.5 | Yes | Clean and Line |  | • Major transverse cracking (>12"), hole in the pipe at lift point, exposed rebar at one joint, joint infiltration, issues with joint offsets and gaskets
2020-01-16 | EP- | 4810 | 48" | RCP | 217.2 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1801 | 18" | RCP | 101.5 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major chips at joints, Major transverse cracking (> 12")
1/26/2020 - 1/27/2020 | EP- | 1802 | 18" | RCP | 194.4 | Yes | Replace |  | • Major chips/broken areas within the pipe
1/26/2020 - 1/27/2020 | EP- | 1803 | 18" | RCP | 210.6 | Yes | Clean and Line |  | • Minor chips, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1804 | 18" | RCP | 211 | Yes | Clean and Line |  | • Minor transverse cracking (< 12"), all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1805 | 18" | RCP | 194 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1806 | 18" | RCP | 202 | Yes | Replace |  | • Major chips, Major transverse cracking (> 12"), and broken areas within the pipe
1/26/2020 - 1/27/2020 | EP- | 1807 | 18" | RCP | 186 | Yes | Clean and Line |  | • Minor cracking/chips in the pipe, all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1808 | 18" | RCP | 186 | Yes | Clean and Line |  | • Minor chips in the pipe, all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1811 | 18" | RCP | 170.5 | Yes | Replace |  | • Major chips in the pipe as well as cracking. Rebar also showing in some locations
1/26/2020 - 1/27/2020 | EP- | 1812 | 18" | RCP | 161.7 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1813 | 18" | RCP | 190.7 | Yes | Clean and Line |  | • Minor chips in the pipe, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1814 | 18" | RCP | 186.1 | Yes | Replace | Potentially Replace | • Potentially could be replaced due to major chips/broken areas at joints • Major chips, Major transverse cracking (> 12"), and broken areas within the pipe • Pipe not listed in overall pipe summary provided by AET
1/26/2020 - 1/27/2020 | EP- | 1815 | 18" | RCP | 136.3 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1815.1 | 18" | RCP | 65.2 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1816 | 18" | RCP | 187 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to broken areas near joints • Major transverse cracking (> 12"), broken areas within pipe, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1817 | 18" | RCP | 188 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1818 | 18" | RCP | 195.6 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1819 | 18" | RCP | 186.8 | Yes | Clean and Line |  | • Minor chips in the pipe, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1820 | 18" | RCP | 179 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major Chips, Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1821 | 18" | RCP | 162.4 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1822 | 18" | RCP | 119.3 | Yes | Clean and Line |  | • Minor chips in the pipe, Major transverse cracking in the pipe (< 12"), all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1823 | 18" | RCP | 80.3 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1824 | 18" | RCP | 81.2 | Yes | Clean and Line |  | • All issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1825 | 18" | RCP | 96 | Yes | Clean and Line |  | • Minor chips in the pipe, all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1826 | 18" | RCP | 121.5 | Yes | Clean and Line |  | • All issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1827 | 18" | RCP | 121.4 | Yes | Clean and Line |  | • Minor chips in the pipe, all other issues are with joint offsets
1/26/2020 - 1/27/2020 | EP- | 1828 | 18" | RCP | 120 | Yes | Clean and Line |  | • Major Chips, Major transverse cracking (> 12"), all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1829 | 18" | RCP | 176 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to major chips at joints • Major Chips, Major transverse cracking (> 12"), erosion in the pipe, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 1830 | 18" | RCP | 179.2 | Yes | Clean and Line | Potentially Replace | • Potentially could be replaced due to hole in the pipe at one location • Major transverse cracking (> 12"), hole in the pipe, all other issues are with joint offsets and gaskets
1/26/2020 - 1/27/2020 | EP- | 3601 | 36" | RCP | 96.1 | Yes | Clean and Line |  | • Major transverse cracking (> 12"), all other issues are with joint offsets
Needs Cleaning | EP- | 1200 | 12" | RCP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
Needs Cleaning | EP- | 1500 | 15" | CMP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
Needs Cleaning | ECMP- | 1800 | 18" | CMP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
Needs Cleaning | EP- | 1810 | 18" | RCP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
Needs Cleaning | EP- | 1842 | 18" | RCP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
Needs Cleaning | EDPI- | 3600 | 36" | DIP | N/A | Yes | Clean and Reinspect |  | Pipe could not be inspected due to debris inside the pipe
[6 empty] | Totals | Retain |  | 2
[7 empty] | Replace |  | 9
[7 empty] | Clean and Line |  | 69
[7 empty] | Clean and Reinspect |  | 6
[7 empty] | Potentially Replace |  | 13