## Sheet1
Task | Start Date | Duration (days) | End Date | PORT ACCESS TERMINAL
SURVEY (CORNERSTONE - WILL INCLUDE OCRM CRITICAL LINE AND WETLANDS FIELD WORK) | 2015-02-15 | 120 | 2015-06-15
R/W STRIP MAPS AND EASEMENT DRAWINGS | 2015-06-15 | 14 | 2015-06-29
ACQUIRE R/W | 2015-06-29 | 123 | 2015-10-30
APPRAISAL | 2015-03-16 | 136 | 2015-07-30
FILE NOTICE OF CONDEMNATION / POSSESSION | 2015-09-01 | 29 | 2015-09-30
SUBMIT OCRM PLAT | 2015-08-03 | 5 | 2015-08-08
OCRM PLAT REVIEW | 2015-08-09 | 30 | 2015-09-08
PREPARE ACOE, OCRM, ARMY CORP B&CB SUBMITTALS | 2015-08-01 | 60 | 2015-09-30
SUBMIT ACOE/OCRM PERMIT | 2015-09-30 | 5 | 2015-10-05
ACOE/ORCM PERMIT REVIEW/APPROVAL (6 MONTHS FROM SUBMITTAL) | 2015-10-05 | 180 | 2016-04-02
ENGINEERING | 2015-02-11 | 292 | 2015-11-30
SOIL BORINGS | 2015-07-15 | 30 | 2015-08-14
GPR (GROUND PENETRATING RADAR) | 2015-09-15 | 30 | 2015-10-15
FAA PERMITS | 2015-10-15 | 90 | 2016-01-13
SCDOT I-26 CROSSINGS AND TRAFFIC CONTROL DESIGN (2 CROSSINGS) | 2015-12-15 | 90 | 2016-03-14
POLE ORDER | 2015-11-01 | 210 | 2016-05-29
CONSTRUCTION | 2016-06-01 | 180 | 2016-11-28
Formulas:
End Date = [Start Date]+[Duration (days)]
End Date = +[Start Date]+[Duration (days)]