## Segment 2 Broad River at I-20
[9 empty] | COST ESTIMATE | [10 empty] | TIMEFRAMES (months) |  |  |  | CLEARANCES (ft) |  |  |  |  | CONSTRUCTION
Utility Owner/ Utility Type | Location | Potential Conflict | RPA Impact Probability | In-Contract |  | Quantities |  |  | Prior Rights |  |  |  |  | Utility Bill
|  |  |  | Yes/ No | $ | Quantity | Unit | Unit Price | Yes/ No/ Partial | SCDOT Share |  | Utility Owner Share |  | SCDOT Share |  | Yes/ No |  |  | Total Cost | Permits | Design | Procurement/ Easement Acquisition | Construction | Structures (bridge piles, footings, noisewalls, MSE, etc.) | Max Fill Limit | Storm Drainage | Other utility owners | Construction Equipment | Seasonal Restrictions | Inside or Outside ROW | Tie-In (In or out of SCDOT project limits) | Items Required to Relocate (Proj ROW, Private Easement, Contractor Activity)
Dominion Power Transmission & Distribution (OH1) | [9 empty] | % | $ | % | $ | % | $ | % |  | $
Overhead Power Lines | Garner Lane - 1 Double Circuit, 3 Single Circuit | Road, C/F | High | No | 0 | 1 | LS | 110000 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Power Lines | Garner Lane | Poles outside of project area, N/A | Low | No | 0 | 0 | EA |  | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Lines | East side of I-20: Light Pole? | Wall Fill | Medium | No | 0 | 1 | EA | 20000 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Lines | Devonwood Drive | Poles outside of project area, N/A | Low | No | 0 | 0 | EA |  | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Lines | East side of I-20 | C/A, pole outside of project area | Low | No | 0 | 0 | EA |  | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Lines | East side of I-20 - _____ KV (Single Circuit?) | Road, C/A, SD | High | No | 0 | 1 | EA | 20000 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Lines | West side of I-20 | Construction Limits | High | No | 0 | 1 | EA | 20000 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Overhead Power Lines | (Broad River Road) - Single Circuit | Road, C/F, C/A, SD, Vertical Profile | High | No | 0 | 20 | EA | 20000 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | 6 | 6 | 10 | 4 | 25 | See profile | 5 | 25 | 30 | none | Both |  | Easement
Dominion Energy Power Distribution (E1)
Underground Power | Broad River Road | Road, C/F, SD | High | No | 0 | 300 | LF | 200 | Partial | 80% | 0 | 20% | 0 |  |  |  | No |  |  | N/A | 8 | 12 | 12 | 20 | 23' under line | 5 | 5 | 15 | None | Both |  | Proj ROW, easement, contractor activity
Underground Power | East Side of Garner Road | Construction Limits | Low | No | 0 | 0 | LF | 200 | Partial | 80% | 0 | 20% | 0 |  |  |  | No
Dominion Energy Gas Distribution (G1)
6" Steel Gas Line | Crossing I-20 | Road, Wall Fill, C/F, SD, C/A | High | No | 0 | 400 | LF | 250 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 6 | 12 | 10 | 10 | 5 | 3 | 10 | None | Inside |  | Proj ROW, easement, contractor activity
2" Steel Gas Line | Broad River Road | Road, C/A, C/F | High | No | 0 | 1200 | LF | 60 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 6 | 12 | 10 | 10 | 5 | 3 | 10 | None | Inside |  | Proj ROW, easement, contractor activity
2" Steel Gas Line | Broad River Road | Construction Limits | Low | No | 0 | 0 | LF |  |  | 0% |  | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 6 | 12 | 10 | 10 | 5 | 3 | 10 | None | Inside |  | Proj ROW, easement, contractor activity
4" Steel Gas Line | Broad River Road | Road, C/A, C/F, SD | High | No | 0 | 500 | LF | 150 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 6 | 12 | 10 | 10 | 5 | 3 | 10 | None | Inside |  | Proj ROW, easement, contractor activity
4" Steel Gas Line | Garner Road | Road, C/A, C/F, SD | High | No | 0 | 550 | LF | 150 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 6 | 12 | 10 | 10 | 5 | 3 | 10 | None | Inside |  | Proj ROW, easement, contractor activity
City of Columbia Water (W1)
24" Water Line Crossing | Crosses over I-20 | Road, C/A, C/F, Wall Fill | High | Yes | 0 | 350 | LF | 300 | Partial |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
12" Water Line | West Side of I-20 starting from Sta. 120+66 up to Broad River Road | Road, C/F, C/A, | High | Yes | 0 | 1700 | LF | 150 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
8" Water Line | Broad River Road crossing over I-20 | Road, C/A, C/F, SD | High | Yes | 0 | 2100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
6" Water Line | North side of Broad River Road | Road, C/A, C/F, SD | High | Yes | 0 | 1900 | LF | 100 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
12" Water Line | Crossing over Broad River Road near I-20 intersection | Road, C/F, C/A | High | Yes | 0 | 120 | LF | 150 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
2" Ductile Water Line | North side of Broad River Road and East side of I-20 | Road, C/F, C/A | High | Yes | 0 | 250 | LF | 80 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
8" Ductile Water Line | Crossing over Broad River Road on East Side of I-20 | Road, C/A, C/F | High | Yes | 0 | 160 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
10" Ductile Water Line | Crossing over I-20 | Road, Guardrail, C/A, C/F | High | Yes | 0 | 160 | LF | 150 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
Unknown Size and Type | Crossing over I-20 | Road, Guardrail, C/A, C/F | High | Yes | 0 | 160 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
6" Ductile Water Line | Crossing over I-20 | Road, Guardrail, C/A, C/F | High | Yes | 0 | 160 | LF | 100 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
8" Water Line | Crossing over Longcreek Drive | Road, C/A, C/F | High | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
City of Columbia Sewer (FS1) (S1)
< 8" TER | Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
8" PV | Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
4" PV | Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
< 8" PV | Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
6" PV | Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
8" TC | Intersection of Broad River Road and Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
6" PV | South side of Longcreek Drive | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
8" TC | Garner Lane | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
< 8" TC | Garner Lane | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
8" TC | Garner Lane up to Apartment Lane | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
6" TC | Garner Lane up to Apartment Lane | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
Unknown Size/Abandoned/Exposed | Crosses I-20 | Road, C/A, C/F, SD, Guardrail | High | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
8" TC | West of I-20 | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
30" TC | West of I-20 | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
30" TC | Crosses I-20 | Outside of project, N/A | Low | Yes | 0 | 0 | LF | [5 empty] | 0
Synergy Utilities (FS3)(S3) - BACKCHECK UTILTY LINES
12" TC | Crossing over I-20 | Road, C/F, Guardrail, SD | High | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
12" TC | East Side of I-20 | C/A, C/F | Medium | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
12" TC | East Side of I-20 | Outside of project limits, N/A | Low | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes |  |  | DBT | DBT | DBT | DBT | 10
10" TC | East Side of I-20 | Outside of project limits, N/A | Low | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes |  |  | DBT | DBT | DBT | DBT | 10
6" PV | West Side of I-20 | C/A, C/F | Medium | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
< 10" TC | West Side of I-20 | C/A, C/F | Medium | Yes | 0 | 100 | LF | 120 | No |  |  |  | 0 | 100% | 0 | 0% | Yes | 0 |  | DBT | DBT | DBT | DBT | 10
10" TC | West Side of I-20 | Outside of project limits, N/A | Low | Yes | 0 | 90 | LF | [5 empty] | 0 |  |  |  | Yes |  |  | DBT | DBT | DBT | DBT | 10
AT&T (T1)(OH7)
Overhead Lines | West side of I-20 | Construction Limits | Low | Yes | 0 | 0 | EA |  |  | 0% |  | 100% | 0
Overhead Telecom Lines | (Broad River Road) - Single Circuit | Road, C/F, C/A, SD, Vertical Profile | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 3 | 6
2 Fiber Lines (144, 12 CT FO) | Crosses over I-20 | Road, Guardrail, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 3 | 6
6-Way 4" Duct Bank
900PR | Crosses over I-20 just South of Broad River Road | Road, Guardrail, Wall, C/F, C/A | High | No | 0 | 2700 | LF | 0 | Partial | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
600PR | Crosses over I-20 just South of Broad River Road | Road, Guardrail, Wall, C/F, C/A | High | No | 0 | 2700 | LF | 0 | Partial | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
(2) 288CT FO | Crosses over I-20 just South of Broad River Road | Road, Guardrail, Wall, C/F, C/A | High | No | 0 | 5400 | LF | 0 | Partial | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
144CT FO | Crosses over I-20 just South of Broad River Road | Road, Guardrail, Wall, C/F, C/A | High | No | 0 | 2700 | LF | 0 | Partial | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
16 Way 4" Duct Bank
(3) 48CT FO | South of Broad River Road crossing over I-21 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
200PR | South of Broad River Road crossing over I-22 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
24CT FO | South of Broad River Road crossing over I-23 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
(3) 144CT FO | South of Broad River Road crossing over I-24 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
(2) 288CT FO | South of Broad River Road crossing over I-25 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
900PR | South of Broad River Road crossing over I-26 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
600PR | South of Broad River Road crossing over I-27 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
72FT CO | South of Broad River Road crossing over I-28 | Road, C/F, C/A, SD | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 6 | 24
Duct bank system | Broad River Road on West Side | Road, C/F, C/A | High | Yes | 0 | 100 | LF | 25 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | DBT | DBT | DBT | DBT
24 CT FO | West side of Broad River Road | Road, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 12 | 24
24 CT FO | West side of Broad River Road | Road, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 12 | 24
Duct bank system | East side of Broad River Road | Road, C/F, C/A | High | Yes | 0 | 100 | LF | 25 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | DBT | DBT | DBT | DBT
48 CT FO | Crossing over Broad River Road on East Side | Road, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 12 | 24
600 PR, 300 PR | Broad River Road continuing to Garner Lane | Road, C/F, C/A, SD | Medium | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 12 | 24
48 CT FO | Broad River Road continuing to Garner Lane | Road, C/F, C/A, SD | Medium | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 6 | 12 | 12 | 24
Spirit Communications (T2)(OH9)
48 CT FO | Broad River Road on West Side | Road, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-4 | 5 | None | Inside |  | Proj ROW, contractor activity
1 1/2" HDPE Coax | Broad River Road on West Side | Road, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-5 | 6 | None | Inside |  | Proj ROW, contractor activity
96 CT FO | Broad River Road on West Side | Road, C/F, C/A | High | No | 0 | 20 | EA | 3260 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-6 | 7 | None | Inside |  | Proj ROW, contractor activity
Duct bank system |  |  |  | Yes | 0 | 1 | LS | 0 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | DBT | DBT | DBT | DBT
MCI/Verizon (T7)(OH10)
2 1/2" Conduit Empty | South of Broad River Road crossing over I-20 | Road, C/F, C/A, SD | High | Yes | 0 | 750 | LF | 25 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | DBT | DBT | DBT | DBT | 5 | 10 | 5 | 3-4 | 5 | Need to confirm | Outside |  | Private easement
Cable | South of Broad River Road crossing over I-20 | Road, C/F, C/A, SD | High | No |  |  |  |  | No | [7 empty] | No
Charter Spectrum CATV (TV1)(OH8)
Overhead Telecom Lines | Garner Lane | Road, C/F | High | No | 0 | 800 | EA | 24 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 4 | 4 | 12 | 5 | 10 | 5 | 2-4 | 5 | Thanksgiving - New Year | Inside |  | Proj ROW, contractor activity
Unknown Size CATV Line | West Side of Broad River Road | Road, C/A, C/F | High | No | 0 | 800 | EA | 24 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 4 | 4 | 12 | 5 | 10 | 5 | 2-5 | 6 | Thanksgiving - New Year | Inside |  | Proj ROW, contractor activity
12 CT FO | West Side of Broad River Road | Road, C/A, C/F | High | No | 0 | 800 | EA | 24 | No | 0% | 0 | 100% | 0 |  |  |  | No |  |  | 2 | 4 | 4 | 12 | 5 | 10 | 5 | 2-6 | 7 | Thanksgiving - New Year | Inside |  | Proj ROW, contractor activity
Duct bank system |  |  |  | Yes |  |  |  |  | No | [7 empty] | No |  |  | DBT | DBT | DBT | DBT