## Segment 1 Colonial Life Blvd
[7 empty] | TIMEFRAMES (months) |  |  |  | CLEARANCES (ft) |  |  |  |  | CONSTRUCTION |  |  |  | COMMENTS
Utility Owner/ Utility Type | Location | Potential Conflict | MSA Impact Probability | In-Contract | Prior Rights | Utility Bill
|  |  |  | Yes/No | Yes/ No/ Partial | Yes/ No | Permits | Design | Procurement/ Easement Acquisition | Construction (months) | Structures (bridge piles, footings, noisewalls, MSE, etc.) | Max Fill Limit | Storm Drainage | Other utility owners | Construction Equipment | Seasonal Restrictions | Inside or Outside ROW | Tie-In (In or out of SCDOT project limits) | Items Required to Relocate (Proj ROW, Private Easement, Contractor Activity)
Dominion Energy Power Transmission & Distribution (OH1)
OH Transmission crossing over I-26 | Sta. 416+00 | Road | Low | No | Yes | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Not anticipated as conflict
3-ph OH crossing over I-26 | Sta. 414+00 | Road | Low | No | Yes | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Not anticipated as conflict
OH Transmission crossing over I-26 | Sta. 423+00 | Road | Low | No | Yes | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Not anticipated as conflict
1-ph, 3-ph OH | McSwain | Road | High | No | Partial | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements
3-ph OH crossing over I-26 | Crossing west of US 378 at I-26 | Off ramp EB US 378 | High | No | Partial | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | To eliminate OH crossing, relocate on McSwain
Secondary feeding sign | Off ramp EB US 378 | New Ramp | High | No | Yes | No | 0 | 3 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Power feed to existing sign. Relocate to new sign
3-Ph OH along Morninghill | Morninghill Road | Road | High | No | Yes | No | 0 | 6 | 18 | 12 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Will attempt to get easements for OH relocation along Morninghill Dr; If not, relocate UG along frontage of homes.
OH Transmission crossings over I-126 | Sta. 38+00 to 40+00 | Road | Low | No | Yes | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements | Not anticipated as conflict
OH Transmission crossings over I-126 | Colonial Life Blvd | Road, Bridge | High | No | Yes | No | 6 | 6 | 12 | 6 | 25 | 18' final clearance | 5 | 5 | 10 | None | Both | Outside | UA, easements
SCE&G Gas Distribution (G1)
2-in PL | McSwain | Road | Low | No | No | No | 2 | 6 | 6 | 4 | 10 | 10 | 5 | 3 | 10 | None | Inside | Inside | Proj ROW, easement, contractor activity | Not anticipating conflict
2-in STL | Lawand Drive | Road, C/F, SD, Wall | High | No | No | No | 2 | 6 | 6 | 4 | 10 | 10 | 5 | 3 | 10 | None | Inside | Inside | Proj ROW, easement, contractor activity
2-in PL | Gracern | Road | Low | No | No | No | 2 | 6 | 6 | 4 | 10 | 10 | 5 | 3 | 10 | None | Inside | Inside | Proj ROW, easement, contractor activity | Not anticipating conflict
2-in STL | Arrowood Road and Crossing Colonial Life Blvd | Road, Guardrail, C/F, SD, C/A | High | No | No | No | 2 | 6 | 6 | 4 | 10 | 10 | 5 | 3 | 10 | None | Inside | Inside | Proj ROW, easement, contractor activity
City of Columbia Water (W1)
8-in | Lawand Drive | Road, Wall, C/A, C/F, SD | High | Yes | Yes | No | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
6-in, 24-in | Along Gracern from Colonial Life to Betsy | Road, C/A, C/F, SD | Low | Yes | No | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW | Assumed no conflicts
8-in | Colonial Life Blvd | Road, C/A, C/F, SD | High | Yes | Partial | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
City of Columbia Sewer (FS1) (S1)
6-in, 8-in PV; <12-in TC; 6-in DIP | Along Morninghill to Lawand Drive | Road, C/F | High | Yes | Partial | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW | See CofC criteria, specs, etc.
6" DIP, 8" PV | Along Gracern from Arrowood to Pump Station | Road, C/A, C/F, SD | Medium | Yes | Partial | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
30-in PCCP | I-126 Ramp D-B over RR to I-26 Sta. 68+50 | Bridge piles | High | Yes | Yes | No | DBT | DBT | DBT | DBT | 25 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
< 8-in, 8-in PV | Colonial Life Ramp A | Road, Guardrail, C/F, C/A, SD | High | Yes | Partial | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
8-in DIP, 8-in PV, <10-in PV | Gracern from Pump Station to Betsy intersection | Road | Low | Yes | No | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
6-in,< 8-in, 8-in, and 12-in. PV, Pump Station | Pump Station at Lawand | Road | High | Yes | Yes | Yes | DBT | DBT | DBT | DBT | 5-10 | See criteria | 5 | 5 | 5 | No | Inside | Both | Proj ROW
City of West Columbia Sewer (FS2) (S2)
3-in, 4-in, 8-in PVC & 16-in TC | Along McSwain and crossing I-26 at Sta. 426+00 | Road, stream, Fill | Low | No | No | Yes | DBT | DBT | DBT | DBT | 5-10 | 10 | 10 | 5 | 10 | None | Both | Inside | Proj ROW, Private easement | Conflict not anticipated; however, if conflict, then DBT will pursue MOA.
City of West Columbia (W2)
2-in, 6-in | McSwain Drive to Holly Hill Drive | C/A,C/F | Low | No | No | Yes | DBT | DBT | DBT | DBT | 5-10 | 10 | 10 | 5 | 10 | None | Both | Inside | Proj ROW, Private easement | It is not anticipated they will be in conflict; however, if they were to be, then DBT will need to pursue MOA.
2-in, 6-in | McSwain Drive from Terrace View to US 378 | C/A,C/F | Low | No | No | Yes | DBT | DBT | DBT | DBT | 5-10 | 10 | 10 | 5 | 10 | None | Both | Inside | Proj ROW, Private easement
AT&T (T1)(OH7)
100pr, 200 pr, 300 pr, 400 pr, 900pr, DB, 24 CT FO | McSwain Road | Guardrail, Road, C/F | Medium | No | No | No | 6 | 6 | 3 | 12 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Adjust guardrail to avoid conflict
600 pr; 24 CT, 216 CT FO | Along I-26 EB from Sta. 420+00 to 438+00; Ramp to US 378 | Road, Stream, C/A, C/F | Medium | No | No | No | 6 | 6 | 3 | 12 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Need to confirm stream relocation.
24CT FO | Morninghill Drive and Bush River Rd. to Lawand Drive | Road, C/F, C/A, SD | High | No | No | No | 6 | 6 | 3 | 8-10 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Timeframes would be concurrent
<100, pr100 pr,and Unkown Size FO | Lawand Drive | Road, C/A, C/F | High | No | No | No | 6 | 6 | 3 | 8-10 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Timeframes would be concurrent
100 pr, 144 CT FO | Along/crossing Colonial Life Blvd. | Road, C/A, C/F, SD | High | No | No | No | 6 | 6 | 3 | 8-10 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW
600 pr; 24 CT, 48 CT, 96, CT, 1/2-in, unknown size FO | Gracern from Arrowood/Colonial Life to I-126 Sta. 68+00 | Road, C/F, C/A | Low | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No impacts were assumed for this area.
Overhead Crossing | Crossing over new ramp onto I-126 from Colonial Life Blvd | Guardrail, Road, C/F | Medium | No | No | No | 6 | 6 | 3 | 8-10 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Timeframes would be concurrent
Overhead Crossing | Crossing over intersection of Arrowood Road and Colonial Life Boulevard | Road, C/F, C/A, Guardrail | High | No | No | No | 6 | 6 | 3 | 8-10 | 3-5 | 10 | 5 | 5 | 5 | None | Inside | Inside | ROW | Timeframes would be concurrent
Spirit Communications (T2)(OH9)
48 CT FO | Morninghill Drive from Bush River Rd to Sta. 9022+00 | Road, C/F, C/A, SD | High | No | No | No | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-4 | 5 | None | Inside | Inside | Proj ROW, contractor activity
144 CT FO | Colonial Life Blvd to West Colonial Life Blvd | Road, C/A, C/F, SD | Medium | No | No | No | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-5 | 6 | None | Inside | Inside | Proj ROW, contractor activity
144 CT FO and unknown size FO | Gracern | Road, C/A, C/F, SD | Medium | No | No | No | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-15 | 16 | None | Inside | Inside | Proj ROW, contractor activity
Lexington Medical Center (T3)
288 CT FO | Lexington Medical Hospital on West side of I-26- outside of project limits | Outside of project limits, N/A | Low | No | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Need to consider as moving item or cost to cure since this is a private owner
Century Link Communications (T4)(OH11)
Overhead Crossing | Colonial Life/ Arrowwood Rd | Bridge | High | No | No | No | 2 | 6 | 4 | 8 | 5 | 10 | 5 | 3-4 | 5 | No | Inside | Inside | Proj ROW | Bore new 3-way HDPE and remove OH 72ct fiber
Unknown Owner Telecom (T8)
144 CT FO | Lexington Medical Hospital on West side of I-26- outside of project limits | Outside of Project Road, N/A | Low | No | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Unk | Need to confirm owner
Charter Spectrum CATV (TV1)(OH8)
OH attachments | Throughout | Road, C/A, C/F, SD | High | No | No | No | 2 | 4 | 0 | 4 | 5 | 10 | 5 | 3-5 | 6 | No | Inside | Inside | Proj ROW, DE Reloc | Need Duke's relocation plans and relocations
UG lines | McSwain, Arrowwood, Gracern | Road, C/A, C/F, SD | Low | No | No | No | 2 | 4 | 0 | 4 | 5 | 10 | 5 | 3-5 | 6 | No | Inside | Inside | Proj ROW
SCDOT (TF1)(E3)
ITS | I-26 Ramp C-A | Road, Bridge | High | No | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | SCDOT to perform ahead of DBT. DBT to coordinate with Ron Hinson.
ITS | I-26 EB &WB | Road, Bridge, C/F | High | No | No | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Department of Administration (TF2)
120 CT FO (2) | I-126 | Road, Bridge, C/F | High | Yes | No | No | DBT | DBT | DBT | DBT | 5 | 10 | 5 | 3-4 | 5 | No | Inside | Inside | Proj ROW